Services & Delivery

Title: Cutover & Migration
Version: v20251023
Owner: Ahsan Kamal
Reviewer(s): Tobias Bessone
Next Review Date: 2026-04-23

1. Introduction

This Cutover & Migration Plan defines Wavetec’s structured methodology for transitioning from legacy or staging environments to full production operation of the Spectra Platform and its associated hardware and software components.

It ensures that all migration, data-loading, and cutover activities are performed in a controlled and auditable manner with zero business disruption, verified checkpoints, and a validated rollback path.
The plan aligns with Wavetec’s global deployment framework and is supported by controls defined in the Project Management Plan, DR/BCP, and Support & SLA documents.

2. Objectives

- Ensure smooth transition from existing to new systems with verified data accuracy and service continuity.

- Conduct parallel operations to validate performance and process integrity before full switch-over.

- Provide rollback capability to restore prior state in the event of critical issues.

- Establish clear ownership, timing, and communication for all migration activities.

- Maintain traceability and audit evidence for compliance and post-implementation review.

3. Governance and Roles

| Role | Responsibility |
| --- | --- |
| Cutover Manager (Wavetec PM) | Leads migration planning, coordinates tasks, and monitors execution. |
| Data Migration Lead | Oversees data extraction, transformation, and loading (ETL). |
| System Owner (Client IT) | Approves data mapping, verifies integrity, and authorizes go-live. |
| Application Lead | Validates functional and interface readiness. |
| Infrastructure Lead | Ensures server, network, and security components prepared. |
| Quality Assurance Team | Conducts pre- and post-cutover validation. |
| Change Control Board (CCB) | Authorizes go-live, rollback, or contingency actions. |

A dedicated Cutover Command Center (CCC) will be activated during go-live week to coordinate tasks, monitor progress, and manage escalations.

4. Migration Scope

- Data Entities: Branch master data, service definitions, user profiles, transaction logs (as per client requirement).

- Applications: Spectra Engine, Spectra Web API, Spectra Management Portal, Web Ticketing, Feedback Web, Lobby Leader.

- Hardware Integration: TDUs, CDUs, kiosks, and signage devices connected to the new environment.

- Infrastructure: Database instances, web services, and authentication servers.

Migration may include both configuration data (master tables) and historical data (transaction logs) depending on client directives.

5. Migration Approach

Wavetec follows a phased migration approach to mitigate risk and ensure complete validation:

| Phase | Description | Key Activities |
| --- | --- | --- |
| Phase 1 – Assessment & Planning | Define migration scope, data sources, and dependencies. | Data inventory, mapping, and cleansing; cutover schedule creation. |
| Phase 2 – Preparation & Mock Migration | Perform dry-run migrations in a test environment. | Validate ETL scripts, measure timing, compare results. |
| Phase 3 – Data Validation & Sign-off | Verify completeness and accuracy of migrated data. | Data-to-data comparison, checksum validation, client approval. |
| Phase 4 – Production Cutover | Execute final migration and switch to production. | Freeze legacy system, perform final data load, confirm services. |
| Phase 5 – Post-Cutover Review | Verify system performance and close migration activities. | Reconciliation, post-go-live monitoring, lessons learned. |

6. Data Loads and Validation

6.1 Data Loading

- Extraction and transformation scripts ensure format consistency with target schemas.

- All ETL processes use secure connections (SFTP/HTTPS) and encryption (AES-256).

- Data loads executed during defined maintenance windows to avoid business impact.

6.2 Validation and Reconciliation

- Record counts, checksum totals, and referential integrity checks performed after every load.

- Random sampling and full-table validation where applicable.

- Discrepancies logged, corrected, and revalidated before sign-off.

- Final Migration Verification Report (MVR) submitted to client for approval.

7. Parallel Run Strategy

To ensure confidence and minimize risk, a parallel run is conducted before full transition.

| Aspect | Details |
| --- | --- |
| Duration | Typically 2–4 weeks depending on transaction volume and complexity. |
| Objective | Validate that new and legacy systems produce identical results for key processes. |
| Scope | Ticket issuance, reporting, appointment scheduling, and queue analytics. |
| Monitoring | Daily reconciliation of transaction counts and service times. |
| Acceptance | Signed parallel run completion certificate upon successful validation. |

During parallel operations, both systems run simultaneously with limited transaction mirroring to verify stability and consistency.

8. Cutover Execution Plan

| Stage | Key Actions |
| --- | --- |
| T-7 Days | Final readiness review, communication of cutover schedule, stakeholder sign-off. |
| T-3 Days | Freeze configuration and master data updates. |
| T-1 Day | Backup legacy system and final mock load verification. |
| Cutover Day (T-0) | Migrate final delta data, activate new environment, execute functional smoke tests. |
| T+1 Day | Begin production support under Hypercare with Wavetec and client IT teams. |
| T+7 Days | Full post-cutover validation and performance certification. |

A Cutover Checklist (CCT-001) is maintained to document completion of every step.

9. Rollback Plan

In the event of a critical failure or data corruption during migration, Wavetec maintains a predefined rollback procedure:

- Decision Point: Triggered by the Cutover Manager in consultation with CCB.

- Rollback Criteria:

  - Failure to meet validation thresholds.

  - Major service disruption with no immediate workaround.

  - Data integrity or loss risk detected.

- Execution:

  - Stop new transactions in Spectra.

  - Restore last verified backup of database and configuration from legacy system.

  - Re-enable legacy services and confirm operational continuity.

- Communication:

  - Notify all stakeholders and record incident under DR/BCP framework.

  - Conduct root-cause analysis and plan re-attempt within 48 hours.

Rollback rehearsals are included in the mock migration phase to ensure procedural readiness.

10. Risk Management and Contingencies

| Potential Risk | Mitigation Strategy |
| --- | --- |
| Data corruption during ETL | Implement checksum and validation rules; maintain encrypted backups. |
| Schedule slippage | Reserve contingency window and parallel testing to absorb delay. |
| Application configuration mismatch | Conduct pre-migration configuration audits. |
| Performance degradation post-cutover | Execute load tests in staging prior to cutover. |
| Incomplete rollback | Maintain verified pre-cutover backups and documented rollback scripts. |

Risk items are tracked in the RAID log under the Project Management Plan.

11. Communication and Coordination

- Cutover Command Center (CCC): Centralized bridge with representatives from Wavetec PMO, Client IT, and Operations.

- Status Updates: Hourly updates during cutover window; end-of-day summary reports.

- Escalation: Any critical issue escalated to Service Manager within 15 minutes.

- Reporting: Post-migration summary report issued within 24 hours of go-live.

12. Acceptance and Handover

The cutover is deemed successful when:

- All data validation reports are signed off.

- Legacy systems are decommissioned or archived.

- No open Severity 1 or 2 issues remain.

- Client issues Production Acceptance Certificate (PAC).

Handover documentation includes:

- Data Migration Report

- Cutover Log

- Parallel Run Summary

- Rollback Verification Checklist

- Lessons Learned Sheet

13. Alignment with Other Deliverables

This plan aligns directly with:

- Implementation Plan — for scheduling and execution sequence.

- Project Management Plan — for RAID and communication governance.

- DR/BCP — for backup and rollback contingency.

- Support & SLAs — for Hypercare response and escalation coverage.

14. Gaps and Assumptions

Gaps

- Specific legacy system interfaces and data schemas are not defined in the uploaded documentation.

- No current cutover schedule or branch sequencing chart available in the project library.

- Client-specific RTO/RPO tolerances during migration window not provided.

- Integration points with third-party APIs for data synchronization not yet mapped.

Assumptions

- Client will provide data extract formats, mapping documents, and legacy system access.

- Data migration will occur during planned maintenance windows with approved downtime.

- Parallel run duration and success criteria will be jointly defined during the planning phase.

- Backups and rollback scripts will be pre-validated by both Wavetec and client IT teams.

- Hypercare phase (post-cutover) will provide 24 × 7 monitoring for the first 7 days.