Services & Delivery

Title: Implementation Plan (Hybrid Model: Predictive for Rollouts; Agile for Software)
Version: v20251023
Owner: Ahsan Kamal
Reviewer(s): Tobias Bessone
Next Review Date: 2026-04-23

1. Introduction

This Implementation Plan describes Wavetec’s delivery approach for deploying its Spectra Platform and associated hardware, software, and services using a Hybrid Project Management Model — combining Predictive (Waterfall) methodologies for hardware rollouts and infrastructure setup, with Agile methodologies for software configuration, customization, and integration.

The objective is to ensure predictable scheduling for physical installations while maintaining flexibility for iterative software development, continuous feedback, and evolving stakeholder requirements.
This model has been successfully applied across Wavetec’s global deployments in banking, telecom, and government sectors.

2. Implementation Objectives

- Deliver fully functional queue management and customer-experience systems that meet all technical, operational, and security requirements.

- Minimize deployment risk through phased planning and controlled rollouts.

- Ensure rapid adaptation to client feedback via agile sprints.

- Establish governance, documentation, and performance reporting across all delivery phases.

- Achieve operational readiness within the contracted timelines and SLAs.

3. Delivery Methodology Overview

Wavetec employs a Hybrid Delivery Model, merging the rigor of traditional project planning with the adaptability of Agile software practices.

| Component | Methodology | Key Deliverables |
| --- | --- | --- |
| Hardware & Infrastructure | Predictive (Waterfall) | Installation schedule, logistics plan, site readiness checklist, commissioning reports |
| Software Development & Configuration | Agile / Scrum | Sprint backlog, user stories, iteration demos, test plans |
| Integration & Testing | Iterative / Hybrid | API integration validation, interoperability tests |
| Training & Go-Live | Predictive with Agile feedback loops | User acceptance testing (UAT) sign-off, knowledge-transfer sessions, operational handover |
| Support & Transition | ITIL-aligned service model | Hypercare report, SLA monitoring dashboard |

4. Governance and Project Organization

Wavetec’s implementation governance structure ensures accountability, visibility, and cross-functional coordination.

| Role | Responsibility |
| --- | --- |
| Project Sponsor | Strategic oversight and approval of project milestones. |
| Project Manager (Client-Facing) | Day-to-day coordination, progress tracking, and stakeholder communication. |
| Technical Lead | Architecture design, integration strategy, and issue escalation. |
| Software Delivery Manager (Scrum Master) | Oversees sprint planning, backlog grooming, and velocity tracking. |
| Hardware Deployment Lead | Manages predictive rollout plan, logistics, and vendor coordination. |
| Quality Assurance Lead | Defines test strategy, acceptance criteria, and performance validation. |
| Change Control Board (CCB) | Reviews scope changes and risk mitigation actions. |

Weekly progress reports and milestone reviews are conducted to maintain alignment with client stakeholders and contractual obligations.

5. Project Phases and Deliverables

5.1 Phase 1 — Project Initiation & Planning

- Kick-off meeting and stakeholder mapping.

- Requirements review and baseline confirmation.

- Creation of the Project Charter, Implementation Schedule, and Risk Register.

- Site survey and infrastructure validation.

5.2 Phase 2 — Hardware Rollout (Predictive)

- Procurement and staging of kiosks, TDUs, CDUs, and signage devices.

- Site preparation, installation sequencing, and factory acceptance testing (FAT).

- Deployment checklist with commissioning verification for each location.

- Delivery milestones tracked through predictive Gantt-based plan.

5.3 Phase 3 — Software Development & Configuration (Agile)

- Sprint 0: Environment setup, backlog definition, and API mapping.

- Bi-weekly sprints including design, build, test, and review cycles.

- Continuous integration (CI) and deployment pipelines ensure tested builds.

- Iterative demos with client product owners for validation.

- Sprint retrospectives to capture improvements and lessons learned.

5.4 Phase 4 — Integration & System Testing

- Integration of Spectra Engine, Web APIs, IAM/SSO, and external systems (CRM/ERP).

- End-to-end validation using predefined test cases and KPIs.

- Load, stress, and performance testing conducted in controlled environments.

- Security and accessibility testing per WCAG 2.1 AA and ISO 27001 frameworks.

5.5 Phase 5 — User Acceptance & Go-Live

- UAT plan executed jointly with client.

- Issue log maintained and tracked to closure.

- Final cutover readiness review.

- Production deployment executed via controlled change window.

- Go-Live report and operational handover signed off.

5.6 Phase 6 — Post-Implementation Support & Transition

- “Hypercare” period (typically 30 days) with dedicated support team.

- Monitoring of incidents, performance, and SLA adherence.

- Transition to Managed Services under Wavetec’s global support structure.

- Knowledge transfer and documentation handover completed.

6. Hybrid Model Governance

| Aspect | Predictive (Rollout) | Agile (Software) |
| --- | --- | --- |
| Planning Horizon | Fixed, milestone-based | Rolling, sprint-based |
| Change Management | Controlled via CCB | Backlog reprioritization |
| Documentation | Detailed upfront | Continuous, lightweight |
| Delivery Cadence | Sequential (phases) | Iterative (sprints) |
| Testing Approach | FAT, SAT, UAT | Continuous integration & testing |
| Stakeholder Engagement | Periodic milestone reviews | Ongoing sprint reviews |

This governance approach ensures predictable hardware delivery timelines while maintaining flexibility for iterative software releases.

7. Tools and Environments

- Project Management: Jira, MS Project, Confluence, SharePoint

- Version Control: GitHub / GitLab

- CI/CD: Jenkins or Azure DevOps

- Testing: Postman, Selenium, JMeter

- Communication: Microsoft Teams, Slack

- Documentation: Wavetec Knowledge Portal with controlled access

All project artifacts are stored in secure repositories following Wavetec’s ISMS controls.

8. Risk Management

A proactive risk-management framework is implemented across all project stages.

| Risk Type | Mitigation Strategy |
| --- | --- |
| Schedule Delays | Predictive milestones with weekly variance tracking. |
| Integration Challenges | Early API testing and continuous client reviews. |
| Scope Creep | Change Control Board authorization required for all variations. |
| Hardware Logistics | Local partner support and pre-deployment site validation. |
| Software Bugs / Regression | Automated testing in every sprint. |
| Dependency on Client Systems | Joint environment readiness sign-off before integration testing. |

Risk logs are reviewed weekly by the PMO and escalated as needed.

9. Communication and Reporting

- Weekly project status reports including progress, risks, and next actions.

- Bi-weekly sprint reviews and demos for software components.

- Monthly steering-committee meetings with client sponsors.

- Real-time dashboards via Jira or Azure DevOps for visibility.

All communications follow Wavetec’s Project Governance Framework, ensuring transparency and traceability.

10. Quality Assurance and Acceptance

- QA integrated across all phases through automated and manual testing.

- Test documentation includes test plans, scripts, and evidence.

- Acceptance criteria defined jointly in UAT stage and approved by client.

- Defect severity classification ensures rapid resolution for critical issues.

11. Training and Knowledge Transfer

- Role-based training delivered to administrators, operators, and supervisors.

- Hands-on workshops and digital training materials provided.

- “Train-the-Trainer” model adopted for scalability.

- Documentation includes user manuals, SOPs, and maintenance guides.

12. Transition to Operations

- Post-Go-Live monitoring and stabilization under the Hypercare phase.

- SLA monitoring dashboards activated.

- Final sign-off document confirms system stability and client satisfaction.

- Transition to long-term support (L1–L3) under Wavetec’s Managed Services.

13. Key Performance Indicators (KPIs)

| Domain | KPI | Target |
| --- | --- | --- |
| Schedule | Milestone adherence | ≥ 95% on-time completion |
| Software Delivery | Sprint velocity stability | ±10% variance |
| Quality | UAT defect closure | 100% prior to Go-Live |
| Availability | Uptime post-launch | ≥ 99.95% |
| Customer Satisfaction | Post-implementation survey | ≥ 90% positive rating |

KPIs are continuously tracked and reviewed in project review meetings.

14. Compliance and Standards Alignment

- ISO/IEC 27001: Information security in project execution.

- ISO 9001: Quality management for delivery processes.

- ISO 22301: Business continuity and operational resilience.

- Agile Manifesto & PMI-PMBOK: Hybrid project management best practices.

- WCAG 2.1 AA & GDPR: Accessibility and data-protection compliance in development.

1. Project Overview (Sample Scenario)

This sample project plan illustrates a typical implementation schedule for deploying:

- 25 Ticketing Kiosks

- 25 Donatello Digital Signage Players

across 5 branches (i.e., 5 kiosks + 5 Donatellos per branch).

This plan assumes:

- No civil works or cabling required

- Branches are already network-ready

- All devices are preconfigured in Wavetec’s staging environment

- Software deployment follows the standard Spectra Cloud model

The objective is to provide a reference implementation template that can be customized for future tenders.

2. High-Level Timeline (Example)

(Total Duration: 10 Weeks)

| Phase | Duration | Dependencies |
| --- | --- | --- |
| Project Initiation | Week 1 | Contract signature, kickoff availability |
| Staging & Pre-Shipment Preparation | Weeks 2–3 | Hardware availability, branch mapping |
| Logistics & Delivery to Sites | Weeks 3–4 | Completed staging & QA |
| Branch Installations (5 branches) | Weeks 4–6 | Deliveries completed per branch |
| Software Configuration (Agile Sprints) | Weeks 1–8 | Environment readiness |
| Integration & Testing | Weeks 6–8 | Installation completion + API access |
| UAT & Training | Weeks 8–9 | Completed SIT |
| Go-Live & Hypercare | Weeks 9–10 | UAT sign-off |

3. Detailed Implementation Plan

3.1 Phase 1 — Initiation & Planning (Week 1)

Activities:

- Kickoff meeting with client and Wavetec teams

- Confirmation of 5-branch deployment structure

- Finalization of delivery locations

- Creation of Project Charter, RACI, Risk Register

- Network readiness confirmation per site (client responsibility)

Dependencies:

- Client provides branch addresses and access windows

- Wavetec provides documentation and site-readiness checklist

3.2 Phase 2 — Staging & Factory QA (Weeks 2–3)

Activities:

- Hardware unboxing, tagging, asset registration

- Firmware updates for all kiosks and Donatello units

- Pre-configuration of:

  - Branch IDs

  - Queue/Service mapping

  - API routing

  - LCD/CDU pairing where applicable

- Bench testing:

  - Ticket printing

  - Media playback

  - Connectivity

  - Heartbeat monitoring

- Packaging for branch-wise deployment

Deliverables:

- Staging report

- Batch-wise asset handover list

Dependencies:

- Hardware availability

- Approved branding assets (logos, colors)

3.3 Phase 3 — Logistics & Distribution (Weeks 3–4)

Activities:

- Shipment of 5 kiosk + 5 Donatello bundles per branch

- Real-time tracking shared with client PM

- Insurance and custom clearance (if applicable)

Dependencies:

- Staging completed

- Client confirms receiving windows

3.4 Phase 4 — On-Site Installation & Commissioning (Weeks 4–6)

Installation Plan Per Branch

| Hardware Per Branch | Time Required | Crew Size |
| --- | --- | --- |
| 5 Kiosks | 1–1.5 days | 2 Technicians |
| 5 Donatello Displays | 0.5–1 day | 1 Technician |

Total per branch: 2–2.5 days

Sequence Per Branch:

- Physical installation & mounting

- Power-on, network connection

- Secure registration with Spectra Cloud

- Real-time connectivity check

- Ticket-printing & display tests

- Branch branding and media upload validations

- Commissioning Sign-Off Report

Branches can be installed in parallel if permitted.

Dependencies:

- Network available at installation spot

- Access to branch during working hours

3.5 Phase 5 — Software Configuration (Weeks 1–8, Agile)

Conducted parallel to hardware rollout.

Sprint 0

- Cloud environment setup

- Service definitions, ticket ranges

- Role/Permission matrix

- Appointment/ticketing configurations

Sprints 1–3

- Dashboard configurations

- Display layouts for Donatello/Web SDU

- Branch-specific rules

- Custom messaging

- Localization

Sprints 4–5

- Integration testing

- Performance optimizations

- Security validation

- Final release package

3.6 Phase 6 — System Integration Testing (Weeks 6–8)

Validations performed:

- Ticket flow end-to-end

- Donatello "Now Serving" display

- Kiosk → Engine → Dashboard propagation

- Operator modes: call, recall, transfer

- SLA thresholds

- Heartbeat monitoring

- Failover scenarios

Deliverables:

- SIT Report

- Issue Log

Dependencies:

- Branch installation must be complete

3.7 Phase 7 — UAT & Training (Weeks 8–9)

Training for:

- Supervisors (Lobby Leader)

- Operators (Web TSU)

- Admins (Portal)

- Branch teams

- IT staff

UAT covers:

- Ticket journeys

- Multilingual flows

- Error scenarios

- Reporting KPIs

Client provides: UAT sign-off.

3.8 Phase 8 — Go-Live & Hypercare (Weeks 9–10)

Go-Live Checklist

- All 5 branches activated

- Queue flows validated

- All Donatello units receiving events

- Ticket printing validated under production load

Hypercare (30 days):

- Daily monitoring

- Fast-response issue resolution

- KPI reporting

- Deployment retrospective

4. Deployment Dependencies (Example)

| Dependency | Responsibility | Notes |
| --- | --- | --- |
| Network availability at branch | Client | Required for kiosk & Donatello pairing |
| Power for hardware | Client | Standard 220–240V |
| Spectra Cloud Environment | Wavetec | For Engine, Dashboard, APIs |
| API credentials | Wavetec / Client | For external integrations if required |
| Branding assets | Client | Logos, color codes |
| Installation access | Client | Branch access windows |

5. Example Milestone Plan (Gantt View Summary)

- M1 – Kickoff Completed (Week 1)

- M2 – Staging Completed (Week 3)

- M3 – Deliveries Completed (Week 4)

- M4 – Branch Installations Completed (Week 6)

- M5 – System Integration Testing Completed (Week 8)

- M6 – UAT Approval (Week 9)

- M7 – Go-Live (Week 9)

- M8 – Hypercare Completed (Week 10)

6. Risks & Mitigations (Sample)

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Branch not ready for installation | High | Pre-deployment site readiness checklist |
| Shipment delays | Medium | Buffer weeks included in logistics plan |
| Integration testing delays | High | Early API testing during Sprint 1 |
| Staff not trained | Medium | Train-the-trainer model |
| Display not receiving events | Low | WebSocket health checks in staging |

7. Summary

This example Implementation Plan showcases:

- A realistic, proven delivery model

- Predictive rollout for hardware

- Agile delivery for software

- Clear dependencies

- Logical branch sequencing

- Risk mitigation

- Full operational readiness

This template can now be re-used and adapted for any tender requiring:

- Hardware + software delivery

- Multi-branch rollout

- Queue management systems

- Digital signage installations

15. Gaps and Assumptions

Gaps

- Specific country or client deployment schedules and resource plans are not included in this generalized version.

- Bid solicitation reference timelines (e.g., in weeks/months) are used only as structural guides.

- Physical site dependencies (network readiness, electrical provisioning) assumed under client responsibility.

- Localization or third-party software dependencies not detailed in uploaded materials.

Assumptions

- Hardware rollout follows a fixed milestone plan managed under predictive scheduling tools.

- Software development uses two-week sprints and integrates continuous deployment pipelines.

- All environments (Development, UAT, Production) are provisioned prior to initiation of testing.

- Wavetec and client teams collaborate through shared governance and change-management mechanisms.

- SLAs for uptime, response, and resolution times follow benchmarks defined in the Non-Functional Requirements and DR/BCP documents.

Services & Delivery

Title: Project Management Plan
Version: v20251023
Owner: Ahsan Kamal
Reviewer(s): Tobias Bessone
Next Review Date: 2026-04-23

1. Introduction

The Project Management Plan (PMP) defines Wavetec’s structured approach to managing the lifecycle of projects delivered under the Spectra Platform framework.
It ensures that all phases — from initiation to closure — are executed with transparency, accountability, and traceability, maintaining compliance with international project management and quality assurance standards (PMI PMBOK 7th Edition, ISO 9001, and ISO 27001).

This PMP establishes a unified structure for risk, issue, and dependency tracking (RAID), stakeholder communication, quality assurance through quality gates, and acceptance testing for deliverable validation.

2. Project Management Objectives

- Establish governance, control, and decision-making mechanisms for the project.

- Ensure risks, issues, and dependencies are actively monitored and resolved.

- Maintain consistent communication between all stakeholders.

- Validate deliverables against defined acceptance criteria and SLAs.

- Provide visibility and documentation at every stage of the project lifecycle.

3. Governance Structure

Wavetec’s governance model provides multi-tier control to ensure efficiency and accountability throughout delivery.

| Governance Level | Key Responsibilities |
| --- | --- |
| Steering Committee | Strategic oversight, escalation management, milestone approval. |
| Project Management Office (PMO) | Schedule, RAID tracking, reporting, budget control. |
| Technical Governance Board | Architectural alignment, design approval, technical risk mitigation. |
| Quality & Compliance Review Board | QA oversight, internal audits, adherence to quality gates. |
| Change Control Board (CCB) | Review and approval of scope, schedule, or cost changes. |

Governance meetings occur weekly (operational), monthly (executive), and at major phase gates (strategic).

4. RAID Management Framework

Wavetec employs a proactive RAID process — Risks, Assumptions, Issues, and Dependencies — maintained in a centralized register and reviewed at weekly PMO meetings.

| RAID Element | Definition | Management Process |
| --- | --- | --- |
| Risks | Potential events that may impact project objectives. | Identified, assessed (probability/impact), mitigated through predefined plans. |
| Assumptions | Conditions accepted as true for planning purposes. | Logged and validated during project review meetings. |
| Issues | Active problems requiring resolution. | Tracked via issue log with owner and target resolution date. |
| Dependencies | Tasks or conditions external to Wavetec’s control. | Managed via dependency log and joint client coordination. |

All RAID items are version-controlled, assigned ownership, and reviewed during weekly governance calls.
Critical risks trigger escalation to the Steering Committee within 24 hours.

5. Communications Plan

5.1 Objectives

- Maintain clear, consistent, and timely communication across all internal and client stakeholders.

- Ensure visibility of progress, risks, and upcoming milestones.

- Enable prompt decision-making and alignment across delivery teams.

5.2 Communication Channels and Frequency

| Communication Type | Purpose | Audience | Frequency | Medium / Tool |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | Initiate project and confirm scope, roles, and milestones. | All stakeholders | Once | Virtual / On-site |
| Weekly Progress Report | Track deliverables, RAID, and KPIs. | Client PM, Steering Committee | Weekly | MS Project / PDF Summary |
| Daily Stand-up | Operational coordination for active streams. | Wavetec Dev/Infra Teams | Daily | Teams / Jira |
| Sprint Review | Present sprint deliverables and gather feedback. | Client PO, PM | Bi-weekly | Teams / Demo |
| Steering Committee Review | Report on progress, budget, and risks. | Senior stakeholders | Monthly | Presentation Pack |
| Change Request Review | Evaluate and approve CRs and variations. | PMO, CCB | As needed | CR Log / Email |

All official correspondence and documentation are archived in the Wavetec Project Repository (SharePoint / Confluence) as part of project recordkeeping.

6. Quality Management and Quality Gates

6.1 Quality Objectives

- Ensure that project deliverables conform to technical, functional, and operational requirements.

- Apply measurable quality metrics throughout the project lifecycle.

- Align with ISO 9001 quality management principles and ITIL service transition standards.

6.2 Quality Gates by Project Phase

| Phase | Quality Gate | Verification Criteria | Approval Authority |
| --- | --- | --- | --- |
| Requirements & Design | Requirements Sign-off | Approved SRS, architecture diagrams | Client + PMO |
| Build / Development | Sprint Review / Code Review | QA checklist, test case coverage ≥ 90% | QA Lead + Scrum Master |
| Integration & Testing | System Test Gate | Pass rate ≥ 95% in SIT/UAT | QA + Client PM |
| Go-Live Preparation | Deployment Readiness Review | UAT sign-off, DR validation, rollback plan | PM + Client Sponsor |
| Closure | Project Acceptance | Delivery against scope, SLA compliance | Steering Committee |

Quality gates act as control points where deliverables must pass predefined criteria before moving to the next phase.

7. Acceptance Testing and Handover

7.1 Acceptance Test Process

- Test Planning: Define acceptance criteria and success measures for each deliverable.

- Execution: Conduct User Acceptance Testing (UAT) in a controlled environment.

- Defect Management: Log and classify issues by severity; re-test after fixes.

- Validation: Confirm system readiness through test reports and sign-offs.

- Handover: Deliver acceptance certificates, documentation, and final operational guide.

7.2 Acceptance Criteria

- 100% of critical test cases passed.

- No open high-severity defects.

- Performance and security tests validated.

- UAT signed off by authorized client representatives.

All acceptance results are stored in the Project Acceptance Register, maintained by the PMO.

8. Change Management Process

Change requests (CRs) are managed under strict control through the Change Control Board (CCB) process.

- Submission: CR logged via standardized form with business justification.

- Impact Analysis: Technical, schedule, and cost impacts assessed.

- Approval: CCB reviews and approves or rejects the change.

- Implementation: Approved CR integrated into the project baseline.

- Documentation: Updated change log shared with all stakeholders.

9. Monitoring, Reporting, and Escalation

- Progress Monitoring: Weekly tracking of milestones, deliverables, and KPIs.

- Dashboard Reporting: Jira and MS Project dashboards for real-time visibility.

- Escalation Hierarchy: PM → PMO → Steering Committee → Executive Sponsor.

- Metrics: RAID closure rate, milestone adherence %, test pass %, and defect density.

All metrics are reviewed at weekly governance meetings to maintain performance transparency.

10. Risk and Issue Management

Each identified risk or issue includes:

- Description and owner.

- Probability and impact rating.

- Mitigation or contingency plan.

- Escalation criteria and timeline.

The PMO maintains the Risk Heatmap, prioritizing high-impact risks and tracking their mitigation progress through closure.

11. Documentation and Configuration Control

All project artifacts (plans, diagrams, test results, change logs, and acceptance records) are version-controlled and stored in a secure, access-controlled repository.
Naming conventions follow Wavetec’s internal configuration policy (e.g., Domain_DocType_vYYYYMMDD_Wavetec.docx).
Access to project documents is restricted by role in accordance with the Identity and Access Management (IAM) policy.

12. Closure and Lessons Learned

- Final review conducted upon project completion.

- Performance metrics compared against original KPIs.

- Lessons learned documented in the Project Retrospective Report.

- Repository archived for compliance and future reference.

13. Compliance and Standards

This PMP aligns with:

- PMI PMBOK (7th Edition) – Process groups and knowledge areas.

- ISO 9001:2015 – Quality Management Systems.

- ISO 27001:2022 – Information Security Management.

- ISO 22301:2019 – Business Continuity.

- ITIL v4 – Service Transition and Change Control best practices.






Sample Timelines and Dependencies

The project is divided into thirteen phases. Each phase contains its own activities, estimated duration, and dependencies that must be satisfied before work can begin.

- Phase 1 – Project Initiation
This phase includes the kick-off meeting, approval of the project charter, identification of stakeholders, and confirmation of the RACI matrix.
Duration: Week 1
Dependencies: Contract signature and availability of client stakeholders.

- Phase 2 – Requirements and Planning
Activities include confirming requirements, validating site readiness, establishing the RAID log, and finalizing the communication plan.
Duration: Weeks 1–2
Dependencies: Completion of initiation activities and receipt of branch details from the client.

- Phase 3 – Solution Design and Configuration
This phase covers solution design, mapping of services, defining user roles and permissions, branding configuration, and preliminary API design.
Duration: Weeks 2–4
Dependencies: Formal sign-off on requirements and identification of all external integrations.

- Phase 4 – Hardware Staging and Quality Assurance
Activities include pre-configuring kiosks and Donatello units, updating firmware, testing ticket printing, validating connectivity, and preparing devices for branch-wise shipment.
Duration: Weeks 3–5
Dependencies: Availability of hardware, branding assets, and network details.

- Phase 5 – Logistics and Delivery
This phase covers hardware shipment to each branch, insurance handling, customs processing when required, and verifying receipt with the client.
Duration: Weeks 4–6
Dependencies: Completion of staging and confirmation of delivery windows by the client.

- Phase 6 – Branch Installation and Commissioning
Activities include physical installation of devices, connecting power and network, registering devices in the system, and performing commissioning tests at each branch.
Duration: Weeks 6–8
Dependencies: Successful delivery of hardware and branch access to installation teams.

- Phase 7 – Software Development and Agile Sprints
This includes configuration of software features, development of integration flows, creating and executing test cases, and conducting sprint reviews with the client.
Duration: Weeks 2–8 (overlapping with other phases)
Dependencies: Requirements confirmed and timely feedback from the client during sprint cycles.

- Phase 8 – System Integration Testing (SIT)
Activities consist of end-to-end flow testing, regression testing, raising and resolving defects, and validating performance.
Duration: Weeks 8–9
Dependencies: Completion of branch installations and readiness of all software components.

- Phase 9 – User Acceptance Testing and Training
This phase includes UAT execution, training for operators, supervisors, and administrators, and delivery of user manuals.
Duration: Weeks 9–10
Dependencies: Successful completion of SIT and availability of UAT environment.

- Phase 10 – Go-Live Preparation
Activities include readiness assessments, validation of rollback and disaster recovery plans, and enforcing a change freeze before production deployment.
Duration: Week 11
Dependencies: UAT sign-off and sponsor approval for deployment.

- Phase 11 – Production Go-Live
This phase activates the system across all branches, monitors live operations, and sets up escalation procedures.
Duration: Week 12
Dependencies: All previous phases completed without outstanding critical issues.

- Phase 12 – Hypercare Support
Activities include daily monitoring, reviewing operational KPIs, resolving issues rapidly, and ensuring system stabilization before handover to support teams.
Duration: Weeks 12–14
Dependencies: Stable production environment and active support resources.

- Phase 13 – Project Closure
This phase concludes the project with final acceptance, performance reviews, documentation archiving, and the lessons learned workshop.
Duration: Week 15
Dependencies: Completion of hypercare and formal client acceptance.

14. Gaps and Assumptions

Gaps

- Client-specific communication escalation matrix and local stakeholder details are not included in this general version.

- Detailed quality metrics (e.g., acceptable defect thresholds by severity) to be finalized during project initiation.

- Local regulatory or documentation retention requirements not specified in the uploaded files.

- RAID tool integration specifics (e.g., Jira or MS Project linkage) assumed but not documented.

Assumptions

- All RAID, change, and acceptance workflows are managed within Wavetec’s PMO framework.

- The project follows hybrid delivery (predictive for rollout; agile for software) as per the Implementation Plan.

- Quality gates and acceptance criteria are aligned with client SLAs and contractual obligations.

- The PMO maintains central responsibility for governance, reporting, and audit traceability.

- Client stakeholders participate actively in UAT and milestone sign-offs.