Services & Delivery

Title: Project Management Plan
Version: v20251023
Owner: Ahsan Kamal
Reviewer(s): Tobias Bessone
Next Review Date: 2026-04-23

1. Introduction

The Project Management Plan (PMP) defines Wavetec’s structured approach to managing the lifecycle of projects delivered under the Spectra Platform framework.
It ensures that all phases — from initiation to closure — are executed with transparency, accountability, and traceability, maintaining compliance with international project management and quality assurance standards (PMI PMBOK 7th Edition, ISO 9001, and ISO 27001).

This PMP establishes a unified structure for risk, issue, and dependency tracking (RAID), stakeholder communication, quality assurance through quality gates, and acceptance testing for deliverable validation.

2. Project Management Objectives

- Establish governance, control, and decision-making mechanisms for the project.

- Ensure risks, issues, and dependencies are actively monitored and resolved.

- Maintain consistent communication between all stakeholders.

- Validate deliverables against defined acceptance criteria and SLAs.

- Provide visibility and documentation at every stage of the project lifecycle.

3. Governance Structure

Wavetec’s governance model provides multi-tier control to ensure efficiency and accountability throughout delivery.

| Governance Level | Key Responsibilities |
| --- | --- |
| Steering Committee | Strategic oversight, escalation management, milestone approval. |
| Project Management Office (PMO) | Schedule, RAID tracking, reporting, budget control. |
| Technical Governance Board | Architectural alignment, design approval, technical risk mitigation. |
| Quality & Compliance Review Board | QA oversight, internal audits, adherence to quality gates. |
| Change Control Board (CCB) | Review and approval of scope, schedule, or cost changes. |

Governance meetings occur weekly (operational), monthly (executive), and at major phase gates (strategic).

4. RAID Management Framework

Wavetec employs a proactive RAID process — Risks, Assumptions, Issues, and Dependencies — maintained in a centralized register and reviewed at weekly PMO meetings.

| RAID Element | Definition | Management Process |
| --- | --- | --- |
| Risks | Potential events that may impact project objectives. | Identified, assessed (probability/impact), mitigated through predefined plans. |
| Assumptions | Conditions accepted as true for planning purposes. | Logged and validated during project review meetings. |
| Issues | Active problems requiring resolution. | Tracked via issue log with owner and target resolution date. |
| Dependencies | Tasks or conditions external to Wavetec’s control. | Managed via dependency log and joint client coordination. |

All RAID items are version-controlled, assigned ownership, and reviewed during weekly governance calls.
Critical risks trigger escalation to the Steering Committee within 24 hours.

5. Communications Plan

5.1 Objectives

- Maintain clear, consistent, and timely communication across all internal and client stakeholders.

- Ensure visibility of progress, risks, and upcoming milestones.

- Enable prompt decision-making and alignment across delivery teams.

5.2 Communication Channels and Frequency

| Communication Type | Purpose | Audience | Frequency | Medium / Tool |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | Initiate project and confirm scope, roles, and milestones. | All stakeholders | Once | Virtual / On-site |
| Weekly Progress Report | Track deliverables, RAID, and KPIs. | Client PM, Steering Committee | Weekly | MS Project / PDF Summary |
| Daily Stand-up | Operational coordination for active streams. | Wavetec Dev/Infra Teams | Daily | Teams / Jira |
| Sprint Review | Present sprint deliverables and gather feedback. | Client PO, PM | Bi-weekly | Teams / Demo |
| Steering Committee Review | Report on progress, budget, and risks. | Senior stakeholders | Monthly | Presentation Pack |
| Change Request Review | Evaluate and approve CRs and variations. | PMO, CCB | As needed | CR Log / Email |

All official correspondence and documentation are archived in the Wavetec Project Repository (SharePoint / Confluence) as part of project recordkeeping.

6. Quality Management and Quality Gates

6.1 Quality Objectives

- Ensure that project deliverables conform to technical, functional, and operational requirements.

- Apply measurable quality metrics throughout the project lifecycle.

- Align with ISO 9001 quality management principles and ITIL service transition standards.

6.2 Quality Gates by Project Phase

| Phase | Quality Gate | Verification Criteria | Approval Authority |
| --- | --- | --- | --- |
| Requirements & Design | Requirements Sign-off | Approved SRS, architecture diagrams | Client + PMO |
| Build / Development | Sprint Review / Code Review | QA checklist, test case coverage ≥ 90% | QA Lead + Scrum Master |
| Integration & Testing | System Test Gate | Pass rate ≥ 95% in SIT/UAT | QA + Client PM |
| Go-Live Preparation | Deployment Readiness Review | UAT sign-off, DR validation, rollback plan | PM + Client Sponsor |
| Closure | Project Acceptance | Delivery against scope, SLA compliance | Steering Committee |

Quality gates act as control points where deliverables must pass predefined criteria before moving to the next phase.

7. Acceptance Testing and Handover

7.1 Acceptance Test Process

- Test Planning: Define acceptance criteria and success measures for each deliverable.

- Execution: Conduct User Acceptance Testing (UAT) in a controlled environment.

- Defect Management: Log and classify issues by severity; re-test after fixes.

- Validation: Confirm system readiness through test reports and sign-offs.

- Handover: Deliver acceptance certificates, documentation, and final operational guide.

7.2 Acceptance Criteria

- 100% of critical test cases passed.

- No open high-severity defects.

- Performance and security tests validated.

- UAT signed off by authorized client representatives.

All acceptance results are stored in the Project Acceptance Register, maintained by the PMO.

8. Change Management Process

Change requests (CRs) are managed under strict control through the Change Control Board (CCB) process.

- Submission: CR logged via standardized form with business justification.

- Impact Analysis: Technical, schedule, and cost impacts assessed.

- Approval: CCB reviews and approves or rejects the change.

- Implementation: Approved CR integrated into the project baseline.

- Documentation: Updated change log shared with all stakeholders.

9. Monitoring, Reporting, and Escalation

- Progress Monitoring: Weekly tracking of milestones, deliverables, and KPIs.

- Dashboard Reporting: Jira and MS Project dashboards for real-time visibility.

- Escalation Hierarchy: PM → PMO → Steering Committee → Executive Sponsor.

- Metrics: RAID closure rate, milestone adherence %, test pass %, and defect density.

All metrics are reviewed at weekly governance meetings to maintain performance transparency.

10. Risk and Issue Management

Each identified risk or issue includes:

- Description and owner.

- Probability and impact rating.

- Mitigation or contingency plan.

- Escalation criteria and timeline.

The PMO maintains the Risk Heatmap, prioritizing high-impact risks and tracking their mitigation progress through closure.

11. Documentation and Configuration Control

All project artifacts (plans, diagrams, test results, change logs, and acceptance records) are version-controlled and stored in a secure, access-controlled repository.
Naming conventions follow Wavetec’s internal configuration policy (e.g., Domain_DocType_vYYYYMMDD_Wavetec.docx).
Access to project documents is restricted by role in accordance with the Identity and Access Management (IAM) policy.

12. Closure and Lessons Learned

- Final review conducted upon project completion.

- Performance metrics compared against original KPIs.

- Lessons learned documented in the Project Retrospective Report.

- Repository archived for compliance and future reference.

13. Compliance and Standards

This PMP aligns with:

- PMI PMBOK (7th Edition) – Process groups and knowledge areas.

- ISO 9001:2015 – Quality Management Systems.

- ISO 27001:2022 – Information Security Management.

- ISO 22301:2019 – Business Continuity.

- ITIL v4 – Service Transition and Change Control best practices.






Sample Timelines and Dependencies

The project is divided into thirteen phases. Each phase contains its own activities, estimated duration, and dependencies that must be satisfied before work can begin.

- Phase 1 – Project Initiation
This phase includes the kick-off meeting, approval of the project charter, identification of stakeholders, and confirmation of the RACI matrix.
Duration: Week 1
Dependencies: Contract signature and availability of client stakeholders.

- Phase 2 – Requirements and Planning
Activities include confirming requirements, validating site readiness, establishing the RAID log, and finalizing the communication plan.
Duration: Weeks 1–2
Dependencies: Completion of initiation activities and receipt of branch details from the client.

- Phase 3 – Solution Design and Configuration
This phase covers solution design, mapping of services, defining user roles and permissions, branding configuration, and preliminary API design.
Duration: Weeks 2–4
Dependencies: Formal sign-off on requirements and identification of all external integrations.

- Phase 4 – Hardware Staging and Quality Assurance
Activities include pre-configuring kiosks and Donatello units, updating firmware, testing ticket printing, validating connectivity, and preparing devices for branch-wise shipment.
Duration: Weeks 3–5
Dependencies: Availability of hardware, branding assets, and network details.

- Phase 5 – Logistics and Delivery
This phase covers hardware shipment to each branch, insurance handling, customs processing when required, and verifying receipt with the client.
Duration: Weeks 4–6
Dependencies: Completion of staging and confirmation of delivery windows by the client.

- Phase 6 – Branch Installation and Commissioning
Activities include physical installation of devices, connecting power and network, registering devices in the system, and performing commissioning tests at each branch.
Duration: Weeks 6–8
Dependencies: Successful delivery of hardware and branch access to installation teams.

- Phase 7 – Software Development and Agile Sprints
This includes configuration of software features, development of integration flows, creating and executing test cases, and conducting sprint reviews with the client.
Duration: Weeks 2–8 (overlapping with other phases)
Dependencies: Requirements confirmed and timely feedback from the client during sprint cycles.

- Phase 8 – System Integration Testing (SIT)
Activities consist of end-to-end flow testing, regression testing, raising and resolving defects, and validating performance.
Duration: Weeks 8–9
Dependencies: Completion of branch installations and readiness of all software components.

- Phase 9 – User Acceptance Testing and Training
This phase includes UAT execution, training for operators, supervisors, and administrators, and delivery of user manuals.
Duration: Weeks 9–10
Dependencies: Successful completion of SIT and availability of UAT environment.

- Phase 10 – Go-Live Preparation
Activities include readiness assessments, validation of rollback and disaster recovery plans, and enforcing a change freeze before production deployment.
Duration: Week 11
Dependencies: UAT sign-off and sponsor approval for deployment.

- Phase 11 – Production Go-Live
This phase activates the system across all branches, monitors live operations, and sets up escalation procedures.
Duration: Week 12
Dependencies: All previous phases completed without outstanding critical issues.

- Phase 12 – Hypercare Support
Activities include daily monitoring, reviewing operational KPIs, resolving issues rapidly, and ensuring system stabilization before handover to support teams.
Duration: Weeks 12–14
Dependencies: Stable production environment and active support resources.

- Phase 13 – Project Closure
This phase concludes the project with final acceptance, performance reviews, documentation archiving, and the lessons learned workshop.
Duration: Week 15
Dependencies: Completion of hypercare and formal client acceptance.

14. Gaps and Assumptions

Gaps

- Client-specific communication escalation matrix and local stakeholder details are not included in this general version.

- Detailed quality metrics (e.g., acceptable defect thresholds by severity) to be finalized during project initiation.

- Local regulatory or documentation retention requirements not specified in the uploaded files.

- RAID tool integration specifics (e.g., Jira or MS Project linkage) assumed but not documented.

Assumptions

- All RAID, change, and acceptance workflows are managed within Wavetec’s PMO framework.

- The project follows hybrid delivery (predictive for rollout; agile for software) as per the Implementation Plan.

- Quality gates and acceptance criteria are aligned with client SLAs and contractual obligations.

- The PMO maintains central responsibility for governance, reporting, and audit traceability.

- Client stakeholders participate actively in UAT and milestone sign-offs.